# EVENT TIMELINE

Contact Cindy Ballard, Event Coordinator, 319-384-2859, 4147 Westlawn, if you need assistance with your event.

## Check these items off your To-Do List when planning your event.

## FOUR TO SIX MONTHS TO A YEAR AHEAD

# Determine the purpose, format and target audience for event

# Create an estimated budget and get approval if necessary

# Select the date, but before confirming it clear the date with calendars; U of I Events calendar, UIF, Office of student Affairs, College of Medicine calendar,  double-check for conflicts with other major functions

- Gather committee/event team (please include Event coordinator)

# Draw up preliminary guest list categories.  Begin collecting addresses for save-the-date mailing, if needed

- Select a name or theme

# Select and reserve a facility

# Develop a rain plan if the event is to be held outdoors

# Reserve a block of hotel rooms, if necessary

# Choose a caterer

- Select and order recognition items (award, honor, citation)

- Order favors, souvenirs, printed folders, and other give-away items

- Reserve rental equipment such as vans, buses, tables, chairs, tents, podiums, etc.

- Confirm program speakers

# Plan presentations

# Get all necessary administrative approvals

# Plan promotion and publicity of event to internal and external audiences

#### TWO TO THREE MONTHS AHEAD

# Write copy, design and get approval of printed invitations and all other printed materials

# Finalize and get approval of the guest list

# Contact Mail Services to coordinate the printed materials mailing (if large quantity mailing)

# Send save-the-date announcements to guests (3-5 months prior to the event)

# Contact program participants and

# Supply suggestions for their remarks

# Gather their biographical information

# Request a photo of each participant for publicity and programs

# Keep campus officials, deans, and administrative officers informed

# Meet or contact UI Parking to discuss parking/shuttle if needed

# Decide on music, book entertainers and talent

# Plan the decorations and color scheme

# Order prizes, novelties, foods, or other special needs

# Contact and/or meet with the florist

# Update security on your plans.  Advise Special Events and Protocol if dignitaries will be invited.

# Begin publicity

# Contact Creative Media Group and photographer or videographer if needed

# Begin creating a logistical outline to document all arrangements as they are decided on and confirmed.

#### TWO MONTHS AHEAD

# Select menus and confirm contract with outside vendor or do a requisition when using IMU or UIHC

# Prepare mailing labels for invitation mailing

# Send out invitations 4 – 6 weeks prior to event (depending on event)

# Finalize decor and facility arrangements

# Make hotel and transportation arrangements for out-of-town dignitaries and guests

# Mail an itinerary to dignitaries

# Prepare, write and print the program

# Finalize the audiovisual presentations

# Order any ceremonial items needed

# Inspect the facility – make sure there are no safety hazards.

# Recruit volunteers to staff registration if needed, such as med student ambassadors and greeters, etc.

# TWO TO FOUR WEEKS AHEAD

# Meet with Event coordinator to go over logistics

# Record and acknowledge RSVPs as they are received

# Mail out confirmations tickets, parking permits, to attendees if necessary

# Ask Facilities for building requests: unlock rooms and floors for date and times.

# Run registration reports for Dean’s and UIF.

# Send detailed instructions to all staff and participants (including tickets, parking permits, and maps)

# Finalize details with caterer, rental company, and all vendors

# Write speeches and introductions, if necessary.

# Do a diagram of the room/building to be used as a seating chart or for set up

# ONE WEEK AHEAD

# Create a Management “day of” schedule outlining all deliveries, etc, and timing for the event

# Print out the guest list in alphabetical order

# Finish place cards, table cards, and/or name tags

# Create the seating chart, if needed.

# Plan a meeting or contact all staff, greeters, ambassadors and volunteers on their duties

# Gather all presentation items such as gifts, plaques, trophies.  Collect ceremonial items.

# Prepare the briefing packet and send along with the guest list to VIPs and Deans (with full names, titles, business and professional affiliations, and other specific interests), biographies, and the final schedule of events to administrative leadership or host

# Deliver prepared introductions, citations, and speeches to those who will read them

# Contact catering with RSVPs and guarantees

# Prepare event box with any supplies, such as tape, string, zip ties, staplers, clip boards, baskets, etc. you may need

# THE BIG DAY

# Arrive early

# Bring the logistical outline, production schedule, directions, phone numbers, food orders, seating charts, name tags, table assignments, guest lists, and the event supply box with you

# Check all facilities

# Set up event venue with tables, signs, awards, etc.

# Conduct sound, computer checks.

# Set up registration.  Be sure it is ready no later than 45 minutes prior to the start of your event.

# Relax and smile!!!!!!!!!

# AFTER THE EVENT

# Send thank you notes to staff, volunteers and vendors

# Finalize billing and prepare final budget, if necessary.

# Conduct event meeting to discuss success or ways to improve in the future

# Survey attendees, if appropriate.

Event Planning Worksheet

EVENT: ________________________________________________________

EVENT DATE: _________________________TIME:_____________________

CATEGORY/THEME: ________________________________________________________

CONTACT PERSON:__________________________PHONE:_____________

MFK/BUDGET: ___________________________________________________

INVITATIONS:

Invites	 (check all that apply)

Email   _______		Formal Invitation	_______

Letter   _______		Map	 _______

RSVP’s ______      	Date for RSVP   _______	Date to Printing _________

Reminder email ______

Invitation list (attach a list of names and addresses)

Alumni					______

Faculty					______

Staff					______

Speaker(s)/Presenters(s)		______

Others:					______

Data pull				______       Group/Area: ______________

Date Invitations to be Mailed		_______

RSVP returned to		______________

Total Invitations to be Ordered/Mailed		_______

Event Location:

Venue:			________________________________

Room Confirmation		__________

Room Setup			__________

Tables			__________

Chairs			__________

Room-cleanup		__________

AV-Sound

PA System		_____

Recording		_____

Music			_____

A/V Equipment	_____

Lighting                      _____

Rentals:

Vendor	______________________   Room Setup  _______________________

Tables			________	Registration table _________

Chairs			________

Stage			________

Risers			________  Location  ____________________________

Tent			________  Size   ________ Location _______________

Program:

Speaker	_____________________________________________

Title of Speaker ___________________________________________

Title of Lecture  ____________________________________________

Letter/Email of Invitation Mailed   _________ 	Date: _________

Photograph speaker	___________

Printed Programs	__________           	Date to printer	______________

Gift/Memento		__________		Cost:	_________

Name Tags		__________

Facilities:

Requisition for clean up  ______________________________	 Date: ________

Contacted for building/rooms to be open _______________	 Date: ________

Photographer:

_______________________________   Date contacted:	__________

Flowers/Decorations:

Centerpieces				_________

Boutonniere(s)				_________

Corsage (s)				_________

Plants					_________

Balloons				_________

Other: ____________________________________________

Catering:

Vendor		_____________________________	(attach a list of catering order or menu)

Contract:				_yes/no___

Breakfast (buffet or served)		__________

Luncheon (buffet or served)		__________

Dinner	(buffet or served)		__________

Hors d’oeuvres				__________

Liquor   (cash bar or open)		__________

Projected Headcount			__________

Event Staff:

Office staff				__________

Student Ambassadors/Tours		__________

Others					__________

Entertainment:			_____________________________________

Mementos/Gift Baskets

Who to Receive	__________________________________

Item			________________________	Cost: _____

Building Hardware for Dedications

Portrait		__________	Ordered ______	Cost:	__________

Plaque		_______				Cost:	__________

Ordered	_______	Vendor: 	______________________

Signage	_______				Cost:	__________

Ordered	_______	Vendor: ___________________________

Publicity:

News Release		__________

Web			__________

Posters		__________

Publications		__________

Signage for building    __________

Parking:

Event Signage		__________

Other			__________

Security		__________

Disabilities Needs:	________________

Supplies needed for event:

Evaluation of Event: