# CAPITAL INVESTMENT REVIEW

NAO Overview:

All proposed major investments shall be assessed by the NOAA Facilities Investment Management Board (FIMB) against the following selection criteria:

- alignment with and support of NOAA’s Mission, Goal, and Strategic Plan Objectives;

- positive return-on-investment (qualitative/quantitative benefits at acceptable costs within acceptable timeframes); and

- risk assessment (at an acceptable level of risk).

The Capital Investment Review concludes with inclusion in the NOAA Program and DOC Step One Notification.

NAO Responsibilities

CAO:

- Makes capital investment recommendations to the FIMB as part of the PPBES process

- Updates the OMB Exhibit 300, as necessary, to reflect latest cost and schedule information

- Prepares analyses and briefing materials for the FIMB

- Schedules and coordinates the FIMB decision point briefing

- Prepares the DOC Step One Notification package

- Seeks and obtains DOC and OMB approvals

- Performs Risk Assessment in conjunction with the Senior Project Manager and the LO Client Representative

- Performs economic analysis using The Automated Prospectus System (TAPS) or equivalent

- Performs OMB Circular A-11 Capital Lease Scoring Analysis, as required

- Oversees the development of macro-level requirements

- Forms the Integrated Project Team

- Maintains the official project file containing FIMB, DOC, and OMB approvals

Line Office:

- Provides input to the OCAO for developing macro-level project requirements

- Assists the CAO in briefing the FIMB

- Ensures AA-level approval in accordance with LO policy

Facility Investment Management Board:

- Provides initial review of proposed investment priorities

Table 2-1 Steps:

CIR-1 Develop Initial Functional Requirements

CIR-2 Develop Initial Schedule

CIR-3 Update Initial Project Cost Estimate

CIR-4 Prepare A-E Programming Study SOW

CIR-5 Task A-E and Issue Notice to Proceed

CIR-6 Approve Programming Study

CIR-7 Identify Alternatives

CIR-8 Analyze Alternatives

CIR-9 Perform Economic (TAPS) Analysis

CIR-10 Update PDRI (if used)

CIR-11 Update OMB Exhibit 300

CIR-12 Conduct Independent Review

CIR-13 Draft Interagency MOA/MOUs, as necessary

CIR-14 Prepare for and Conduct FIMB Review

CIR-15 Prepare for and Conduct DOC RPRB Briefing

CIR-16 Approval to Proceed to Scoping

## Initial Functional Requirements

3.1.1  Feasibility Study or Equivalent.  One of the optional steps prior to determining initial functional requirements is to examine the issues that will make the project feasible or unfeasible, and in some cases to determine the best strategy for proceeding with the project. The following may be addressed in a Feasibility Study:

- Needs assessment:  identify agency requirements, reference space standards, and planning considerations. This assessment is used to articulate changing client mission, changing client housing requirements, deterioration in asset condition, and decline in asset financial performance.  It should be performed in sufficient detail to clearly define a goal/required outcome.  What are the expected benefits of the proposed facility?

- Budget and scope of the project:  whether or not the proposed project work can be accomplished at the target budget.

- Site analysis: Is the site chosen suitable?  Is it zoned for the project?  Are there sufficient parking, utilities, etc.?  Must the facility be in a particular location, and if so why?  What is the relationship to existing or proposed facilities?

- Strategy for developing the project on a given site.

- Optimal size and type of building.

- What will be required in the way of soils tests, seismic upgrades, etc.?

- How will other site considerations, such as sound levels, traffic, etc., affect the project?

- Are there any toxins or hazardous materials to be dealt with?

- What other cost, planning, schedule, and design constraints might the project run into?  What milestone dictates the need for this capability in the requested fiscal year?  What is the impact of delay?

- Preparation of a report which documents all of the findings of the study and makes recommendations for proceeding with the next steps of the project.

3.1.2  MOUs/MOAs.  See Appendix B for Sample Formats.

## Program of Requirements

### Programming

[Program of Requirements]

[Programming Study]

##### The Program of Requirements Document expands upon the Facility Concept Study, emphasizing the detail project description by room/area.  This document includes the results of any studies that have been completed and provides detailed criteria (e.g., size, location, environmental) for each of the rooms, activities, or functions included in the facility.  The project’s PDRI documentation is also included in the Program of Requirements.

Programming is the process used to arrive at the set of criteria on which the design is based, and by which it is later evaluated.  The programming phase is where the project is built—not brick by brick, but decision by decision.  This is the time when a common vocabulary for the project is created, and preferences and requirements are determined and built into the overall picture before time is invested in design.

One of the most important purposes of the program is to reduce the need for later backtracking and redesign.  A thorough programming process is essential for maintaining an orderly and cost-effective design process later in the project.  PPMD goes through a detailed list of criteria with the client, looking for program needs that translate into square footage or other design requirements.

Programming usually involves a meeting or series of meetings. In the programming meetings, the client’s specific goals, priorities, and uses for the spaces are discussed in detail.  PPMD encourages the client to consider all important issues up front, help the client understand the ramifications of their decisions, and make recommendations based on past experience and professional knowledge.  All of the requirements of the project are then put into a clearly-organized written program which will be a reference throughout the design process.

If, however, the client would like to play a less active role in establishing the program, PPMD can develop a complete project program for the client’s review based on our experience designing numerous NOAA facilities.

Items specifically analyzed in the programming phase typically include the following:

- Goals, needs, limitations, expectations, aesthetics.

- Scope of work: the number of occupants; size of the building; number of rooms; room adjacencies.

- Activities to occur in each room and outdoor area.

- Safety and security requirements.

- Existing and new utility locations and requirements.

- Site context: Weather, noise, solar access, vehicular access, handicap accessibility, sense of entry, site analysis.

- Codes and regulations.

- Budget and priorities: Preliminary cost analysis usually based on area and/or volume, to be refined later.

- Project Scheduling.

- In the case of reusing an existing building: Carefully document and evaluate present building and its conditions. Determine what can be reused, what must be discarded, what must be rebuilt.

The A/E shall collect detailed technical, spatial, and programmatic requirements for interior and exterior facility spaces, including architectural and engineering needs; analyze program functions, access/circulation, security; project budget estimates; preliminary assessment for LEED certification (checklist); presentation of findings and recommendations; providing and evaluating spatial relationships of program elements with block diagrams, stacking diagrams, circulation/space flow diagrams, adjacency diagrams, space plans and other analyses prior to design. Other specific requirements for submissions and presentations may be further defined in the Program of Requirements SOW.

## Economic (TAPS) Analysis or Equivalent

3.3.1  Requirement.  OMB Circular A-94 requires a formal economic analysis of government programs and projects.

TAPS was developed for GSA as a model to perform consistent present value cost analysis of alternative procurement methods to meet the space and facility requirements of the government.  Because TAPS is one of a few readily available off-the-shelf applications which can be tailored to meet A-94 requirements, it has been recommended for use by DOC.  However, in many cases, the added features embedded in the TAPS model do not apply to the NOAA alternatives.  CAO has therefore developed internal formats to handle such cases.

3.3.2  Differences between TAPS and CAO Analyses.

Cases vs. Alternatives.  TAPS allows selection of up to six Prospectus Types:  Lease, Construction, Repair and Alteration (R&A), Purchase, Lease with an Option to Purchase (Lease-Option), or Construction-Leaseback.  Four different alternatives (or scenarios) for each of the Prospectus types are allowed, for a maximum of 24 cases.

- Interim Housing.  TAPS accommodates interim housing within a case through its irregular housing module.

- Building Reversion.  Building reversion, if and when applicable, is automatically calculated within TAPS.  However, reversion apparently cannot be removed from a Build or Repair & Alteration case.

- Depreciation and FFE.  TAPS-XL calculates accelerated depreciation and tax savings on furniture, fixtures and equipment or any other personal property provided by the lessor.  Given that NOAA provides all FFE for its owned and leased facilities, depreciation of FFE does not apply.  The TAPS-XL model can accommodate non-depreciation of FFE by either not entering a value in the FFE data entry cell, or changing the FFE depreciation rate.  However, it is simpler not to address depreciation at all outside the TAPS model.

- Lease Escalation.  TAPS applies the general rate of inflation to the Net Net Rent on an annual basis.  However, TAPS cannot accommodate any periodic increases in Rent within the same case.  It is possible that TAPS could accommodate rent increases by creating a separate case; however, the two cases would need to be added together in some manner, possibly outside of TAPS.   It is therefore easier to apply periodic rent increases outside the TAPS model.

- One time costs.  One time costs other than those identified by TAPS data fields are difficult to handle.  Demolition, for example, can be handled in a variety of ways, but does not retain its label in TAPS.

- Summary Sheets.  Within TAPS, the output summary sheets are static – there are no formulas.  One can copy the output into a new spreadsheet and attempt to reverse engineer the solution, but such an approach is very time consuming and ineffective.

- Sensitivity Analysis and Viewing Results.  In TAPS, one must enter the change on the data entry sheet and populate the case in order to see results.  While doable, this approach is somewhat unwieldy.

## Independent Review

For extremely complex and/or large projects, an Independent Review Panel may be convened at the direction of the CAO.  During the Capital Investment Review segment, the project requires an independent review of program, functional, and facility requirements.  Once selected and convened, the independent panel will verify the mission need; validate the programmatic and facility requirements; validate technical, cost, and schedule baselines; and assesses the overall status of project planning resources to execute the project.

In the absence of, or inconsonance with an Independent Review, the PDRI will still be used.  See Section 1.6 for a detailed discussion of the PDRI.

## Facilities Investment Management Board (FIMB)

The NOAA Executive Panel (NEP) fulfills the role of the FIMB.  On an annual basis, the NEP will be briefed on the Facilities Modernization Plan update at the end of the PPBES Planning Phase to meet the requirements of OMB Circular A-11 with regard to Agency oversight and approval of projects selected for advancement.

OMB Exhibit 300s will be prepared for projects advancing from the Programming Phase to the Budgeting Phase.

## DOC Real Property Review Board (RPRB)

See Appendix A.